## Schedule2022
Data Engineer Course From 01/03/2022 To 31/03/2022
whizlab: | duynguyenkhuongvn@gmail.com/default | Please don't share or publish these accounts to external
itexams: | duynguyenkhuongvn/default | Expected output: AZ-900
Udemy: | https://fpt-software.udemy.com/ | duynkFX14156@funix.edu.vn |  |  | Khuongduy123 |  |  |  |  | 779539950
LinkedIn | https://www.linkedin.com/learning/ | ID: 1115241106751 |  |  | Pass: 3698 |  |  |  |  | 742419000
37120950
No. | Training Outline | Content | Duration (days) |  | Start date | Finish date | Progress
|  |  | Plan | Actual |  |  | Phat | Thien | Hoa | 236376630
Course 1: Microsoft Azure Exam AZ-900 Certification |  |  | 12 |  | 2022-01-03 | 16/3/2022 |  |  |  | 153393345
1 | Introduction | Online study | 1 |  |  |  | 100% | 100% | 100% | 155907990
2 | Understand Cloud Concepts | Online study | 1 |  |  |  | 100% | 100% | 100% | 545677965
a | Sharing: Introduce Data engineer | Sharing
3 | Understand Azure Core Services - Part 1 | Online study | 2 |  |  |  | 75% | 75% | 75%
4 | Understand Azure Core Services - Part 2 | Online study | 2 |  |  |  | 75% | 75% | 50%
b | Sharing: Introduce ETL | Sharing
5 | Understand Security , Privacy , Compliance and Trust | Online study | 2 |  |  |  | 25% |  | 50%
6 | Understand Azure Pricing and Support | Online study | 1 |  |  |  |  | 75% | 25%
7 | Practice Tests | Online study | 3 | [5 empty] | 10%
c | Sharing: Introduce working process | Sharing
Course 2: Exercise Spark Transformation on Azure |  |  | 10 |  | 17/3/2022 | 31/3/2022
d | Sharing: | Sharing
1 | Using Azure Data Factory (ADF) to move data | Exercise | 3
2 | Write a Spark job using Scala | Exercise | 3
3 | Use ADF to transform data to a table in Data Warehouse | Exercise | 2
4 | Storage access keys should be stored in Azure Key Vault | Exercise | 2
Course 7: Final Present

## Present
No | Fullname | First present |  | Final present
|  | Title | Time | Title | Time
1 | Nguyen Thi To Nhu | Introduce about MapReduce | 2021-07-07
2 | Nguyen Thi Nhu Y | Introduction to Big Data and Hadoop

## Exercise
Deployment BackEnd (BE) use flask-api
A | Extract
1 | Load data from CSV to dataframe
B | Transfer
1 | Check NA "price" column
2 | Check length "drive-wheels": if >5 then remove
3 | Check "Height, Width, Length, Engine-size, Bore, Stroke, Price" datatype: if not interger then remove
4 | Check duplicate
5 | Rename column "Fuel-type" to "type", "Num-of-cylinders" to "Num_cylinders"
6 | Anonimize "dayUpdate" column to "1"
C | Load
1 | Insert Validated data into SQL(raw table) and save bad record to csv in local
2 | Normalize database to 3NF
3 | Create store procedure and trigger to load data to RAW table and Native tables

## Schedule
[9 empty] | Done | Blocked | Learning
Data Science Course From __/__/2020 To __/__/2021
|  | Udemy acc: |  |  |  |  | ticaids18l12@gmail.com/Udemy@123L12 |  | Please don't share or publish these accounts to external
|  | Coursera acc: |  |  |  |  | thangtran.com@gmail.com/12345678x@TMA
No. | Training Outline | Content | Duration (days) |  | Start date | Finish date |  |  | Progress
|  |  | Plan | Actual |  |  |  | Van | Vươn | Hơn | Như
Course 0: Python basic for Data Engineer |  |  | 5 day |  | 22/2/21 |  | https://www.udemy.com/course/python-coding/ |  | Done |  | Start date: 01/06/21
1 | Expression and variables | Online study | [5 empty] | Done | Done | Done | Done
2 | Data structures: String, list, tuples, set, dictionary | Online study |  |  |  |  | https://www.programiz.com/python-programming/variables-constants-literals | Done | Done | Done | Done
3 | File I/O Handling | Online study |  |  |  |  | https://www.programiz.com/python-programming/variables-datatypes | Done | Done | Done | Done
4 | Conditions, branching and iterationc | Online study |  |  |  |  | https://www.programiz.com/python-programming/if-elif-else | Done | Done | Done | Done
5 | Functions, Packages | Online study |  |  |  |  | https://www.programiz.com/python-programming/function | Done | Done | Done | Done
6 | Objects and Classes | Online study |  |  |  |  | https://www.programiz.com/python-programming/class | Done | Done | Done | Done
7 | OOP in Python (Optional) | Online study |  |  |  |  | https://www.programiz.com/python-programming/object-oriented-programming | Done | Done | Done | Done
8 | Python Pandas | Online study |  |  |  |  | https://www.tutorialspoint.com/python_pandas/index.htm | Done | Done | Done | Done
https://www.learndatasci.com/tutorials/python-pandas-tutorial-complete-introduction-for-beginners/
https://www.geeksforgeeks.org/pandas-tutorial/ (Tham khảo)
(Down về) https://drive.google.com/drive/u/1/folders/1sVo4juC6XerK2rcw6_W-Q4hnBwi16LSe
9 | Python Numpy | Online study | [5 empty] | Done | Done | Done | Done
(Down về) https://drive.google.com/drive/u/1/folders/1sVo4juC6XerK2rcw6_W-Q4hnBwi16LSe
10 | Python Matplotlib | Online study |  |  |  |  | https://www.w3schools.com/python/numpy_getting_started.asp | Done | Done | Done | Done
(Down về) https://drive.google.com/drive/u/1/folders/1sVo4juC6XerK2rcw6_W-Q4hnBwi16LSee
11 | Python code examples (Tham khảo) | Online study |  |  |  |  | https://www.programiz.com/python-programming/examples (Tham khảo)
Course 1: Databases and SQL/NoSQL for Data Science |  |  | 2 day |  | 2021-03-01 |  | https://www.coursera.org/learn/sql-data-science/home/welcome | Done | Done
| Presentation of mentor | [5 empty] | https://bytescout.com/blog/20-important-sql-queries.html
1 | Introduction to Databases and Basic SQL | Online study |  |  |  |  | https://www.w3schools.com/sql/ | Done | Done | Done | Done
2 | Advanced SQL | [5 empty] | https://www.hackerrank.com/domains/sql | Done | Done | Done | Done
3 | Accessing Databases using Python | Online study |  |  |  |  | https://www.datacamp.com/community/tutorials/tutorial-postgresql-python | Done | Done | Done | Done
4 | Course Assignment | Online study |  |  |  |  | https://stackabuse.com/working-with-postgresql-in-python/ | Done | Done | Done | Done
After a course | [9 empty] | Done
Course 2: Hadoop Architecture |  |  | 3 day |  | 2021-03-03 |  |  | Done | Done
Presentation of mentor
1 | Introduction to Big Data and Hadoop | Online study |  |  |  |  | https://data-flair.training/blogs/hadoop-tutorial/ | Done | Done |  | Done
2 | Hadoop Architecture | Online study |  |  |  |  | https://data-flair.training/blogs/hadoop-architecture/ | Done | Done |  | Done
3 | Distributed Storage (HDFS) | Online study |  |  |  |  | https://data-flair.training/blogs/hadoop-hdfs-tutorial/ | Done | Done |  | Done
4 | YARN | Online study |  |  |  |  | https://data-flair.training/blogs/hadoop-yarn-tutorial/ | Done | Done |  | Done
After a course
Course 3: Distributed Processing |  |  | 7 day |  | 2021-03-08 |  |  | Learning | Done
1 | Introduction to MapReduce | [5 empty] | https://data-flair.training/blogs/hadoop-mapreduce-tutorial/ | Done | Done |  | Done
2 | MapReduce Data Flow | Online study |  |  |  |  | https://data-flair.training/blogs/hadoop-mapreduce-flow/ | Done | Done |  | Done
3 | How to MapReduce Work | [5 empty] | https://data-flair.training/blogs/how-hadoop-mapreduce-works/ | Done | Done |  | Done
4 | Apache Hive | Online study |  |  |  |  | https://data-flair.training/blogs/apache-hive-tutorial/ | Done | Done |  | Done
5 | NoSQL Databases - HBase | Online study |  |  |  |  | https://data-flair.training/blogs/hbase-tutorial/ | Done | Done |  | Done
After a course
Course 4: Bigdata With Programming Languages |  |  | 7 day |  | 2021-03-17 |  |  | Done | Done
1 | Basics of Functional Programming and Scala/Python | Online study | [5 empty] | Done | Done |  | Done
2 | Apache Spark Next Generation Big Data Framework | Online study | [5 empty] | Done | Done |  | Done
3 | Spark Core Processing RDD | Online study | [5 empty] | Done | Done |  | Done
4 | Spark SQL - Processing DataFrames | Online study | [5 empty] | Done | Done |  | Done
5 | Spark MLLib - Modelling BigData with Spark | Online study | [5 empty] | Done | Done |  | Done
6 | Stream Processing Frameworks and Spark Streaming | [6 empty] | Done | Done |  | Done
7 | Spark GraphX | [6 empty] | Done | Done |  | Done
After course
Course 5: Azure Cloud Service
1 |  | Online study
2 |  | Online study
3 |  | Online study
After course
Course 6: AWS Cloud
1 |  | Online study
2 |  | Online study
3 |  | Online study
4 |  | Online study
After course
Course 7: Final Project
Presentation of mentor

## Online Resource
STT | Title | Link
Math | The Art of Statistics: How to Learn from Data | https://drive.google.com/drive/folders/1ZWHisw__6gFD-98yBWyKg_QFd5yb1ufp?usp=sharing
Math | Machine Learning cơ bản | https://sachvui.vn/wp-content/uploads/2021/07/sachvui-vn-machine-learning-co-ban-pdf-1.pdf
Math | Algebra | https://drive.google.com/drive/folders/1ewj7R2oT5mkKWUSouWJoR04kbFpsM_fb?usp=sharing
Math | Calculus | https://drive.google.com/drive/folders/1jASHm9w3QlgiJSFL5PWy0kpFNcjOFsQ_?usp=sharing
System | Learning Spark with DataBricks | https://pages.databricks.com/rs/094-YMS-629/images/LearningSpark2.0.pdf
System | Scala and Spark for Big Data Analytics | https://drive.google.com/drive/folders/1KfAsuyESNq5ePdtXSawFfxI7M2qwXkg4?usp=sharing
System | Software Design Patterns ( Theory + Java examples code) | https://drive.google.com/drive/folders/1M3yq2bIlfr0zVTMjFkZBt0kdpPg7xoaO?usp=sharing
System | Realtime System | https://drive.google.com/drive/folders/12HDd3yzi5twJntsu5jpjILtCvYpN_u06?usp=sharing
System | Distributed System | https://drive.google.com/drive/folders/1Katl--RlxwtxcIEBv-Rl1ND7irxSU7Rl?usp=sharing
System | Computer Architecture | https://drive.google.com/drive/folders/1CoJepsAYbL4QFcp8bJwnglCaSOG5wXUC?usp=sharing
Data protection | Data protection | https://drive.google.com/drive/folders/1qWdFuOwRKSvuJiBCqkx2TZiQoMkrBMm5?usp=sharing